## Sheet1
Student Names |  | Luciana | Vaishnavi | Anamika | Phoebe | Hiroko | Next
2021-02-08 | Topic Worked on | Make sure what to do next
| Activity/Outcome | Phoebe - Describe the dataset Anamika - Include a sample data in the notebook and explain it Vaish - Write our project's objective Hiroko - Explain how the algorithm works Luciana - Explain the hyper parameters |  |  |  |  | Next: understand each part and prepare for that by next lab (Feb 12)
| Attendance Participation | Yes | Yes | Yes | Yes | Yes
2021-02-08 | Topic Worked on | Decide the order of presentation and work on to make each part's explanation
| Activity/Outcome | Check the details about parameter with Masoud, and create the script for explanation of hyper parameter | Make sure the objectives with Masaoud and create the script. (Plus: Tensorflow explanation) | Make sure the details about sample data with team members, and create the script | Make sure the entire project with Masoud, and create dataset script | Make sure the details of algorithm with team members, and create the script | Next: understand each steps, parameters, and data by Feb 18, then show each part deliverables on Friday (Feb 19)
| Attendance Participation | Yes | Yes | Yes | Yes | Yes
2021-02-08 | Topic Worked on | Make sure how to explain the algorithm, extra code, and prediction
| Activity/Outcome | Explained some scenarios and additional code to get more accurate data. Also, discussed how to divide the tasks for the presentation. Until next Friday, she needs to create one notebook that is used in the presentation. | Explained some additional codes to test and train more efficiently. Discussed the order and the responsibility of the presentation. By next Wednesday, share the script. | Explained some additional codes that are useful for training and testing. Discussed the order and the responsibility of the presentation. By next Wednesday, share the script. | Explained the accuracy score categorized by 5 parameters. Discussed how to separate the role of the presentation. By next Wednesday, share the script. | Explained the accuracy score from three parameters' perspective. Discussed who is in charge of the presentation. By next Wednesday, share the script. | Next: By Wednesday (hopefully Monday?) share the script. Then, Luciana will make onenote for the presentation.
| Attendance Participation | Yes | Yes | Yes | Yes | Yes